## Sheet1
Defect ID | Test Case ID | Module Test | Description of Defect | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity | Status | Comments
D001 | TC002 | Form Validation | Last Name field mandatory not enforced | Leave Last Name blank and submit | N/A | Should show error “Last Name is mandatory” | Login successful | High | Open | Mandatory message not displayed
D002 | TC003 | Form Validation | Typo in Phone number placeholder | Focus on Phone field | N/A | Placeholder should read “Phone number” | Placeholder shows “Phone nunber” | Minor | Open | Needs correction
D003 | TC004 | Form Validation | Phone number field accepts letters | Enter letters in Phone number | abcdef | Should show validation error | Text accepted | High | Open | Validation not enforced
D004 | TC007 | Form Validation | Email field mandatory not enforced | Leave Email blank and submit | N/A | Should show error “Email is mandatory” | Login successful | High | Open | Can login without email
D005 | TC008 | Form Validation | Email format validation not enforced | Enter invalid email | fuzayel@com | Should show error “Enter valid email” | Email accepted | High | Open | Invalid email accepted
D006 | TC010 | Form Validation | Password masking not working | Enter password | mypass123 | Should display masked characters | Password visible | Medium | Open | Password not masked
D007 | TC014 | Form Submission | Form allows submission with invalid data | Fill form with invalid email and short phone | Ozih uddin, al fuzayel, 123, BD, fuzayel@com, password123 | Form should show validation errors | Form submitted successfully | High | Open | Validation not working
D008 | TC015 | UX | Mandatory field note missing or incorrect | Check note “All fields marked with * are mandatory” | N/A | Note visible | No * in First name | Minor | Open | UX note missing